## Summary
Project | Amount
AJT:Sale Incentive System | #REF!
Total | #REF!

## Manday-Interface
Project Name | Sale Incentive System
Customer | AJT
Task | #Total Day | PM | SA | BA | Developer | Designer | QA/Documentor | System Admin | Remark
|  | #Day | #Day | #Day | #Day | #Day | #Day | #Day
AJT-Sale Incentive System
1. Planning | 0
1.1 Gathering Requirements | 0
- Requirement Sale Incentive Policy Clarification (TT & LAOS Channels) | 3 | 1 | 1 | 1 |  |  | 0
- Requirement Sale Incentive Policy Clarification (MT & SI Channels) | 3 | 1 | 1 | 1 |  |  | 0
- Requirement Sale Incentive Policy Clarification (Prorate, GD, Special Adjustment) | 3 | 1 | 1 | 1 |  |  | 0
1.2 Produce Business Requirements Document (SRS and High Level Design) | 4 | 0 | 2 | 2 |  |  | 0
1.3 Confirm Business Requirement and Conceptual Design | 1.5 | 0.5 | 0.5 | 0.5 |  |  | 0
2. Design Phase | 0
2.1 Requirement Workshop + Policy Clarification (TT & LAOS Channels) | 4.5 | 0.5 | 1 | 2 |  |  | 1
2.2 Requirement Workshop + Policy Clarification (MT & SI Channels) | 4.5 | 0.5 | 1 | 2 |  |  | 1
2.3 Requirement Workshop + Policy Clarification (Prorate, GD, Channels) | 4.5 | 0.5 | 1 | 2 |  |  | 1
2.4 Solution Architecture + Interface Contract (K2/SmartObject/SP/SSRS) | 1.5 | 0.5 | 1 | 0 |  |  | 0
2.5 K2 Workflow + Smart Form Design (ทุก flow) | 2.5 | 0.5 | 2 | 0 |  |  | 0
2.6 SP Calculation Engine + .NET API Interface Design Spec | 3.5 | 0.5 | 3 | 0 |  |  | 0
2.7 DB Model Finalization + Stored Procedure Design | 2 | 0 | 2 | 0 |  |  | 0
2.8 SSRS Report Format Design (For HR, Trace Report) | 3 | 0 | 1 | 2 |  |  | 0
2.9 SIT/UAT Test Strategy + Test Case Design | 10.5 | 0.5 | 2 | 4 |  |  | 4
2.10 Produce Detail Design Document (DDS) | 4 |  | 4 | 0 |  |  | 0
Sign Off #1 - Completed Requirement and Design | 0
3. Development Phase | 0
3.1 K2 Master Data Forms (Period, M_Month, Parameters, Rate Tables) | 5.5 |  | 0.5 | 0 | 5 |  | 0
3.2 K2 Import Data (DWH / HCM + Validation Gate trigger) | 7 |  | 1.5 | 0.5 | 5 |  | 0
3.3 K2 Approval Workflow | 7 |  | 0.5 | 1.5 | 5 |  | 0
3.4 K2 Main Transaction Forms (Incentive Entry, Calculation Result View, Core Function UI) | 20 |  | 3 | 2 | 15 |  | 0
3.5 SmartObject + SP Common Infrastructure | 9.5 |  | 1.5 | 0 | 8 |  | 0
3.6 Core Functional | 0
- Function Validation Gate Engine (Period/Hierarchy/Mapping checks) | 10 |  | 1.5 | 0.5 | 8 |  | 0
- Function MT/SI Calculation Engine (Mapping + Cascade 4 Level) | 19.5 |  | 2.5 | 2 | 15 |  | 0
- Function TT Calculation Engine | 10.5 |  | 1.5 | 1 | 8 |  | 0
- Function LAOS Calculation Engine | 10.5 |  | 1.5 | 1 | 8 |  | 0
- Function GD Special Incentive Engine (4 products × step payout) | 10.5 |  | 1.5 | 1 | 8 |  | 0
- Function Fixed Rate Engine (Job Function lookup → fixed amount) | 6 |  | 1 | 1 | 4 |  | 0
- Function Prorate Logic Engine | 11.5 |  | 1.5 | 2 | 8 |  | 0
- Special Adjustment Config + Before/After Audit | 7.5 |  | 1.5 | 1 | 5 |  | 0
- For HR Output Generation (Variable + Fixed, M_Month mapping) | 7 |  | 1 | 1 | 5 |  | 0
- Audit Trail + Parameter Change Logging | 5 |  | 1 | 0 | 4 |  | 0
3.7 System Interface | 0
- .NET Core API Interface — External System Integration (DWH / HR Import) | 6 |  | 2 | 0 | 4 |  | 0
- .NET Core API Interface — External System Integration (HR Output Export) | 6 |  | 2 | 0 | 4 |  | 0
3.8 Reports | 0
- SSRS Reports (For HR print form + Calculation Trace Report) | 8 |  | 1 | 2 | 5 |  | 0
- Dashboard (Achievement summary, by channel/dept/period) | 8 |  | 1 | 2 | 5 |  | 0
3.9 SIT (Internal) | 0
- Testing Form / Workflow Bug Fixing | 6 |  | 0 | 0 | 3 |  | 3
- Testing Calculation Validation & Bug Fixing | 10 |  | 0 | 0 | 5 |  | 5
- Testing Reports & Bug Fixing | 6 |  | 0 | 0 | 3 |  | 3
4.Stabilizing Phase | 0
4.1 Deploy to QA Environment | 7 | 1 | 2 | 1 | 2 |  | 1
4.2 SIT - Common Platform (K2 forms, workflow, import, auth) | 10.5 | 0.5 | 2 | 2 | 4 |  | 2
4.3 SIT - Channel Calculation Engines (MT/TT/SI/LAOS + GD + Fixed) | 14.5 | 0.5 | 2 | 3 | 6 |  | 3
4.4 User Acceptance Testing (UAT) + Defect Fix (End to End Test) | 21 | 1 | 4 | 4 | 8 |  | 4
4.5 Regression Test + Performance Check | 11 | 1 | 2 | 2 | 4 |  | 2
Sign Off # 2 - Completed UAT | 0
5. GoLive Phase | 0
5.1 Training Power Users & End User | 12 | 2 | 2 | 2 | 4 |  | 2
5.2 Training Administrators | 5 | 1 | 1 | 1 | 1 |  | 1
5.3 Deploy to Production Environment | 7 | 1 | 2 | 1 | 2 |  | 1
5.4 Support 3 months | 20 | 0 | 5 | 5 | 5 |  | 5
Sign Off #3 - Go Live! | 0
Total Number of Manday per each Role |  | 15 | 73 | 57 | 176 | 0 | 39 | 0